## DEFECT TRACKER
DEFECT / ISSUE TRACKER
[5 empty] | User Impact | Business impact
Status | Count |  |  | 1-Critical | 1 | 0
1-New | 0 |  |  | 2-High | 0 | 1
2-Open | 0 |  |  | 3-Medium | 1 | 1
3-Closed | 0
4-Fixed | 0 |  |  | 4-Low | 0 | 0
TOTALS | 0 |  |  |  | 2 | 2
Defect ID | Detected Date | Updated Date | Req Id | Status | Severity | Priority | Title | Module | Version | Build | Duplicate ID | Reported by | Steps to reproduce | Screenshot | Expected Result | Actual Result | Environment | Customer facing update | Internal Update | Assigned to
1 | 2026-02-27 | 2026-02-27 | 101 |  | 3-Medium | 3-Medium | User is unable to scroll to home page footer due to dynamic load of image | Home page Module | 1 | 11 |  | QA -Rahul | 1. Given on home page 2.When tries to scroll to Footer 3.Then unable to reach Footer | ss_02 | Able to reach footer | unable to reach footer | stage | No update from customer till now |  | Rajat Bansal
2 | 2026-03-08 | 2026-03-08 | 102 |  | 1-Critical | 2-High | Coupon "SAVE50" applied for order value below500. | Cart\Coupon discount Module | 1 | 11 |  |  | 1.Open the food App website 2. add an item worth rs499to the cart 3. navigate to the cart page . 4. applied the coupon code SAVE50. 5.observed the discount applied |  | 1.The app should display a validation message such as coupon SAVE50 is applicable only for orders above500rs. 2.The coupon should not be applied, and the cart value should remain 499. | 1.The coupon SAVE50 is successfully applied even though the order value is rs 499. 2.The app deducted rs 50, making the final price rs449. | QA |  |  | Engineer & PM
Engineer
Engineer
PM & Engineer for LOE
3 | 2026-03-08 | 2026-03-08 | 102 |  | 1-Critical | 2-High | User can access dashboard and order history using browser back button after logout | Authentication Module | 1 | 11 |  |  | 1.Open the application. 2.login with valid credentials. 3.Navigate to the dashboard page. 4.Go to order history . 5.Click on logout. 6.After logout, press the browser back button. |  | The User should be redirected to the login page , the system should not allow access to the dashboard or the order history after logout. | The dasboard page loads again, and the user is able to view order history without logging in. | QA

## screenshot
Screenshot Id | Screenshot
ss_02

## Dropdowns
Status
1-New
2-Open
3-Closed
4-Fixed
[Blank]
Severity
1-Critical
2-High
3-Medium
4-Low
[Blank]